## 2021-11-26
Weeknr | Week 48 |  |  |  |  | Week 49 |  |  |  |  | Week 50 |  |  |  |  | Week 51 |  |  |  |  | Week 52 |  |  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Week | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8
Uren | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Test microSD | V | V
Test LEDs |  |  | V
Ontwerpen toetsmodule |  |  |  | V
Wachten op levering toetsmodule
Solderen toetsmodules
Ontwerpen moederbord | [6 empty] | V | V
Wachten op levering moederbord
Solderen moederbord
Bestellen laatste onderdelen | [11 empty] | V
Wachten op laatste onderdelen
MP3s nodig
Maken software
Mechanica nodig
Inbouwen
Vergaderen | [19 empty] | V
Vergeten (20%)